## 01 Detailed Implementation
#REF!
Implementation Plan
Task ID | Who? | When? | Done? | Device | Action/command | Effect on Service
SOE.001 |  | Pre-implemenation | Yes |  | Obtain Lync Dialog Listener certificate from customer
SOE.002 |  | Pre-implemenation | Yes |  | Install certificate into cert store on designated server and validate attributes as well as private key attachment
SOE.003 |  | Pre-implemenation | Yes |  | Ensure "Network Service" has "Full control" and "Read" permissions to manage the private key of the certificate | Allows application enhanced key usage for explicit control of client authentication with network controllers
SOE.004 |  |  |  |  | Assign Certificate to Lync Dialog Listener
SOE.005 |  | Implementation |  | FE-ServerXX | Stop the Skype Dialog Listener Service with the below command:
SOE.006 |  | Implementation |  | FE-ServerXX | Get-Service -Name "Skype for Business Dialog Listener" ¦ Stop-Service
SOE.007 |  | Implementation |  | FE-ServerXX | Navigate to SDN installation directory, in this case the path below:
SOE.008 |  | Implementation |  | FE-ServerXX | E:\Program Files\Microsoft Skype for Business Server\Microsoft Skype for Business Dialog Listener
SOE.009 |  | Implementation |  | FE-ServerXX | Open the configuration file "DialogListener.exe.config"
SOE.010 |  | Implementation |  | FE-ServerXX | Find the line in the file which reads <add key="configurationcertificate"
SOE.011 |  | Implementation |  | FE-ServerXX | Change the value of this key paramater to be the thumbprint of the new certificate.
SOE.012 |  | Implementation |  | FE-ServerXX | Save the changes to the file and close
SOE.013
SOE.014 |  |  |  |  | Backup SDN Manager listeners and subscribers
SOE.015 |  | Implementaion |  | SDN-ManagerServer | First take a backup of the SDNManager subscribers, listeners and manager configuration using the commands below, SDNmanager.exe is case sensitive.
SOE.016 |  | Implementaion |  | SDN-ManagerServer | Get list of subscribers first so we can reference the identifiers:
SOE.017 |  | Implementaion |  | SDN-ManagerServer | .\SDNManager.exe /d s
SOE.018 |  | Implementaion |  | SDN-ManagerServer | Backup each subscriber using command below:
SOE.019 |  | Implementaion |  | SDN-ManagerServer | .\SDNManager.exe /d s <identifier> $env:USERPROFILE\desktop\SDN-Subscriber01.xml
SOE.020 |  | Implementaion |  | SDN-ManagerServer | Get list of listeners so we can reference the identifiers:
SOE.021 |  | Implementaion |  | SDN-ManagerServer | .\SDNManager.exe /d l
SOE.022 |  | Implementaion |  | SDN-ManagerServer | Backup each listener using command below:
SOE.023 |  | Implementaion |  | SDN-ManagerServer | .\SDNManager.exe /d l <identifier> $env:USERPROFILE\desktop\SDN_Listener_Pool.xml
SOE.024 |  | Implementaion |  | SDN-ManagerServer | Copy the the SDNManager.exe.config file to a safe location for backup purposes
SOE.025
SOE.026 |  |  |  |  | Update client certificate thumbprint in SDN Running config
SOE.027 |  | Implementation |  | SDN-ManagerServer | Use the commands below to update the client certificate thumbprint for the listener pool:
SOE.028 |  | Implementation |  | SDN-ManagerServer | .\SDNManager.exe /p l <identifier> clientcertificateid=<NewCertThumbprint>
SOE.029 |  | Implementation |  | FE-ServerXX | Start Dialog Listener service on all Front Ends in affected pool using below command:
SOE.030 |  | Implementation |  | FE-ServerXX | Get-Service -Name "Skype for Business Dialog Listener" ¦ Start-Service
SOE.031
SOE.032
SOE.033
SOE.034
SOE.035
SOE.036 |  |  |  |  | Conduct Test Plan
SOE.037
SOE.038
SOE.039
SOE.040
SOE.041
SOE.042
SOE.043
SOE.044
SOE.045
SOE.046
SOE.047
SOE.048
SOE.049
SOE.050
SOE.051
Note on G5: If the device you are making a change on does not appear in this list, then you didn't add it to the Impact and Risk Assessment. Go back and add it, and it will become available for selection here.

## 02 Test Plan
#REF!
Test Plan
|  |  |  | PRE-CHANGE |  | POST-CHANGE |  | POST ROLLBACK
Test ID | Service | Test Description | Expected Result | Actual Result | Successful? | Actual Result | Successful? | Actual Result | Successful? | Comments
TP.001 |  | Ensure Skype for Business Dialog Listener service is running | Service is operational |  | Yes
TP.002 |  | Ensure SDN Manager service is running on SDN Manager server | Service is operational |  | Yes
TP.003 |  | Ensure log files on the LDL (Front End) servers do not contain error messages indicating issues accessing SDN after implementation and service restart. | No log messages indicating connectivity issues |  | Yes
TP.004
TP.005
TP.006
TP.007
TP.008
TP.009
TP.010
TP.011
TP.012
TP.013
TP.014
TP.015
TP.016
TP.017
TP.018
TP.019
TP.020
TP.021
TP.022
TP.023
TP.024
TP.025
TP.026
TP.027
TP.028
TP.029
TP.030
TP.031
TP.032
TP.033
TP.034
TP.035
TP.036
TP.037
TP.038
TP.039
TP.040
TP.041
TP.042
TP.043
TP.044
TP.045
TP.046
TP.047
TP.048
TP.049
TP.050
Note on I4: Execute the Test Plan if the change was successful or if the backout was invoked. Record initials against each test as it is performed
Note on K4: Helpful Hint: This would only be filled in should a rollback be required.
Note on D5: Helpful Hint: Not listed? You can only test items involved in your change - if you're testing something its because there is an impact upon it within your change. Please ensure that everything involved in your change is listed on the Impact Assessment tab.
Note on E5: Helpful Hint: Detail the test to be taken. Write this so that a novice could perform the test. If a username or password is required mention where it can be found or include it, if appropriate.
Note on F5: Helpful Hint: Explain what the result should be. Make it clear and unambiguous so there is a definitive "yes" or "no" answer to whether the test was successful or not.
Note on G5: Helpful Hint: If the Actual Result meets the Expected Result you don't necessarily need to capture anything here. Putting Yes or No in the "Successful" box would be more than sufficient. There's no need to add paperwork when it adds no clarity!
Note on H5: Helpful Hint: Was the test successful? Yes or No. If you need to add Comments, use the box on the right.
Note on I5: Helpful Hint: If the Actual Result meets the Expected Result you don't necessarily need to capture anything here. Putting Yes or No in the "Successful" box would be more than sufficient. There's no need to add paperwork when it adds no clarity!
Note on J5: Helpful Hint: Was the test successful? Yes or No. If you need to add Comments, use the box on the right.
Note on K5: Helpful Hint: If the Actual Result meets the Expected Result you don't necessarily need to capture anything here. Putting Yes or No in the "Successful" box would be more than sufficient. There's no need to add paperwork when it adds no clarity!
Note on L5: Helpful Hint: Was the test successful? Yes or No. If you need to add Comments, use the box on the right.

## 03 Detailed Backout
#REF!
Backout Plan
Task ID | Who? | When? | Done? | Device | Action/command | Effect on Service
BO.001 |  |  |  |  | RESTORE CLIENT CERTIFICATE THUMBPRINT FOR DIALOG LISTENER POOL ON SDN MANAGER SERVER
BO.002 |  | Rollback |  | SDN-ManagerServer | Issue the below command to the SDN Manager via Powershell or Command Prompt to REMOVE the current Listener Pool identifier:
BO.003 |  | Rollback |  | SDN-ManagerServer | .\SDNManager.exe /r l SINFEPOOL01.ARC.BTONECLOUD.COM
BO.004 |  | Rollback |  | SDN-ManagerServer | Upload the backed up Listener poool to SDN Manager config via the below command:
BO.005 |  | Rollback |  | SDN-ManagerServer | .\SDNManager.exe /u l SINFEPOOL01.ARC.BTONECLOUD.COM $env:USERPROFILE\desktop\SDN_Listener_SINFEPOOL01.xml
BO.006 |  |  |  |  | Note: No need to stop or start service for above steps
BO.007 |  |  |  |  | RESTORE OLD CLIENT CERTIFICATE THUMBPRINT ON DIALOG LISTENER (FRONT END) SERVERS
BO.008 |  | Rollback |  | FE-ServerXX | Stop the Dialog Listener service with the command below:
BO.009 |  | Rollback |  | FE-ServerXX | Get-Service -Name "Skype for Business Dialog Listener" ¦ Stop-Service
BO.010 |  | Rollback |  | FE-ServerXX | Open the configuration file "DialogListener.exe.config" located at the below file path on the Font End servers:
BO.011 |  | Rollback |  | FE-ServerXX | E:\Program Files\Microsoft Skype for Business Server\Microsoft Skype for Business Dialog Listener
BO.012 |  | Rollback |  | FE-ServerXX | Find the line in the file which reads <add key="configurationcertificate"
BO.013 |  | Rollback |  | FE-ServerXX | Change the value of this key paramater to be the thumbprint of the OLD certificate.
BO.014 |  | Rollback |  | FE-ServerXX | Save the changes to the file and close
BO.015 |  | Rollback |  | FE-ServerXX | Restart the Dialog Listener service with the below commands:
BO.016 |  | Rollback |  | FE-ServerXX | Get-Service -Name "Skype for Business Dialog Listener" ¦ Start-Service
BO.017
BO.018 |  |  |  |  | CONDUCT TEST PLAN
BO.019
BO.020
BO.021
BO.022
BO.023
BO.024
BO.025
BO.026
BO.027
BO.028
BO.029
BO.030
BO.031
BO.032
BO.033
BO.034
BO.035
BO.036
BO.037
BO.038
BO.039
BO.040
BO.041
BO.042
BO.043
BO.044
BO.045
BO.046
BO.047
BO.048
BO.049
BO.050
Note on F5: If Back-out is required, enter your initials to show this line item was completed